## Sheet1
Week	Date	Activities	Subactivities	Time (half day)	Sum of hours
10	28.02.22	Organization	First contact	0.5	2	Organization	68	Report	44
11	07.03.22	Organization	Gantt Diagramm (early state)	0.5	4
12	14.03.22	Analysis	Research about RTK	0.5	6
13	21.03.22	Organization	Meeting (Marcos)	0.125	6.5	Analysis	0
13	21.03.22	Organization	Logical Diagramm (early state)	1	10.5	EFM-113B	21
14	28.03.22	Organization	Meeting (Antonio)	0.125	11
14	28.03.22	Organization	Gantt Diagramm	1	15
14	28.03.22	Organization	Logical Diagramm (early state)	0.5	17
15	04.04.22	Analysis	Research about EFM-113B	0.5	19
16	11.04.22	Analysis	Research about RTK	0.5	21
16	11.04.22	Organization	Meeting (Antonio)	0.125	21.5
17	18.04.22	Analysis	Research about RTK	0.5	23.5
18	27.04.22	Organization	Meeting (Marcos)	0.125	24
18	27.04.22	Analysis	Research about RTK	0.5	26
19	02.05.22	Organization	Writing requirements of thesis	0.5	28
20	09.05.22	Organization	Meeting (Marcos)	0.125	28.5
20	09.05.22	Organization	Gantt Diagramm	0.5	30.5
21	16.05.22	Analysis	Research about RTK	1	34.5
21	20.05.22	Organization	Meeting (Marcos)	0.125	35
22	23.05.22	Organization	Meeting (Marcos)	0.125	35.5
22	25.05.22	Organization	Laboratory’s visit	0.25	36.5
23	30.05.22	EFM-113B	Installation of RPI + AD	0.25	37.5
24	06.06.22	Pause	Pause	0	37.5
25	13.06.22	Organization	Meeting (Marcos)	0.125	38
26	20.06.22	Organization	Report	2	46
26	23.06.22	Organization	Report	1	50
26	24.06.22	Analysis	Research about EFM-113B (EPFL)	2	58
26	25.06.22	Organization	Report	1	62
27	30.06.22	EFM-113B	Make circuit	2	70
27	01.07.22	EFM-113B	Test circuit	2	78
27	02.07.22	Organization	Report	1	82
28	04.07.22	Organization	Report	1	86
28	05.07.22	EFM-113B	Test circuit	1	90
28	05.07.22	Organization	Report	2	98
28	06.07.22	Organization	Report	2	106
28	06.07.22	Organization	Meeting (Sebastien Guillaume)	0.25	107
28	07.07.22	Organization	Report	1	111

				27.75