## Planned
|  |  |  | Dependency | Estimated time [h] | 9 | 9 | 10 | 11 | 12 | 13 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | Counted time [h]
1.0 | Analyze |  |  |  | 8 | [39 empty] | 0
1.1 | EFM-113B |  |  |  | 8 | [39 empty] | 0
1.1.1 |  | Reading datasheet |  |  | 8 | 15: 2; 16: 2; 17: 2; 18: 2; 21: 2 | 8
1.2 | RTK |  |  |  | 24 | [39 empty] | 0
1.2.1 |  | Reading about material and implementation |  |  | 16 | [39 empty] | 16 | bar: 10 to 11; 12 to 18; 19 to 25
1.2.2 |  | Reading about other projects |  |  | 4 | 24: 2; 25: 2 | 4
1.2.3 |  | Choosing equipment |  | 1.2.1, 1.2.2 | 4 | 28: 2; 29: 2 | 4
1.3 | Other sensors | [43 empty] | 0
1.3.1 |  | Thermometer | [42 empty] | 0
1.3.1.1 |  |  | Reading about material and implementation |  | 2 | 36: 2 | 2
1.3.1.2 |  |  | Choosing equipment | 1.3.1.1 | 2 | 36: 2 | 2
1.3.2 |  | Hygrometer | [42 empty] | 0
1.3.2.1 |  |  | Reading about material and implementation |  | 2 | 36: 2 | 2
1.3.2.2 |  |  | Choosing equipment | 1.3.2.1 | 2 | 37: 2 | 2
1.3.3 |  | Barometer | [42 empty] | 0
1.3.3.1 |  |  | Reading about material and implementation |  | 2 | 37: 2 | 2
1.3.3.2 |  |  | Choosing equipment | 1.3.3.1 | 2 | 37: 2 | 2
2.0 | EFM-113B |  |  |  | 32 | [39 empty] | 0
2.1 | Making circuit |  |  |  | 32 | [39 empty] | 0
2.1.1 |  | Design |  | 1.1 | 8 | 26: 6; 27: 2 | 8
2.1.2 |  | Software implementation |  | 2.1.1 | 8 | 26: 4; 27: 4 | 8
2.1.3 |  | Tests & Verification |  | 2.1.1, 2.1.2 | 16 | 27: 4; 28: 12 | 16
3.0 | RTK |  |  |  | 160 | [39 empty] | 0
3.1 | Implementation |  |  |  | 160 | [39 empty] | 0
3.1.1 |  | Software implementation |  | 1.2.3 | 80 | 29: 16; 30: 16; 31: 16; 32: 16; 33: 16 | 80
3.1.2 |  | Tests & Verification |  | 3.1.1 | 80 | 29: 8; 30: 8; 31: 8; 32: 8; 33: 8; 34: 16; 35: 16; 36: 8 | 80
4.0 | Drone |  |  |  | 16 | [39 empty] | 0
4.1 | Battery selection |  |  | 2.1.3, 3.1.2 | 4 | 34: 4 | 4
4.2 | System protection |  |  | 4.1 | 8 | 35: 8 | 8
4.3 | Model selection |  |  | 4.2 | 4 | 35: 4 | 4
5.0 | Other sensors |  |  |  | 24 | [39 empty] | 0
5.1 | Thermometer |  |  |  | 8 | [39 empty] | 0
5.1.1 |  | Software implementation |  | 1.3.1 | 4 | 37: 4 | 4
5.1.2 |  | Tests & Verification |  | 5.1.1 | 4 | 37: 4 | 4
5.2 | Hygrometer |  |  |  | 8 | [39 empty] | 0
5.2.1 |  | Software implementation |  | 1.3.2 | 4 | 38: 4 | 4
5.2.2 |  | Tests & Verification |  | 5.2.1 | 4 | 38: 4 | 4
5.3 | Barometer |  |  |  | 8 | [39 empty] | 0
5.3.1 |  | Software implementation |  | 1.3.3 | 4 | 39: 4 | 4
5.3.2 |  | Tests & Verification |  | 5.3.1 | 4 | 39: 4 | 4
5.0 | Organization |  |  |  | 202 | [39 empty] | 0
5.1 | Report |  |  |  | 120 | 12: 4; 13: 4; 26: 12; 27: 12; 28: 12; 34: 4; 35: 4; 36: 4; 37: 8; 38: 16; 39: 20; 40: 20 | 120
5.2 | Guides and graphs |  |  |  | 32 | 27: 4; 28: 4; 34: 2; 35: 2; 36: 6; 37: 2; 38: 4; 39: 4; 40: 4 | 32
5.3 | Meetings |  |  |  | 38 | [39 empty] | 38 | bar: 9; 10 to 40
5.4 | Planning |  |  |  | 12 | 10: 2; 11: 4; 22: 1; 23: 1; 26: 2; 27: 2 | 12
| TOTAL |  |  |  | 478 | 1 | 0 | 4 | 6 | 1 | 1 | 6 | 6 | 2 | 4 | 4 | 4 | 4 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 25 | 29 | 31 | 27 | 25 | 25 | 25 | 25 | 27 | 35 | 25 | 25 | 29 | 33 | 25 | 478
|  |  | Days (8 hours) |  | 59.75 | 0.125 |  | 0.5 | 0.75 |  |  | 0.75 | 0.75 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.375 | 0.375 | 0.5 | 0.5 | 3.125 | 3.625 | 3.875 | 3.375 | 3.125 | 3.125 | 3.125 | 3.125 | 3.375 | 4.375 | 3.125 | 3.125 | 3.625 | 4.125 | 3.125 | 58.75